## Pre-drywall inspection checklis
Job / address
Walked by
Date
With
Section | Check | Result | Notes | Photo #
Before you start | Plans, electrical layout and selections on hand
Before you start | Rough inspections passed (framing, electrical, plumbing, mechanical)
Before you start | Insulation not yet installed
Framing | Studs straight and plumb, nothing split or cracked
Framing | Headers over every window and door
Framing | Window and door openings sized for the units ordered
Framing | Notches and holes within limits, or repaired
Framing | Hangers, straps and hold-downs fully nailed
Framing | Blocking for cabinets, grab bars, TV, handrails and towel bars
Framing | Fireblocking where required
Framing | No water stains on sheathing or roof deck
Electrical | Every box where the plans put it, at the planned height
Electrical | Boxes set out for the finished wall (thicker for tile)
Electrical | Cables stapled, not crushed, nail plates where needed
Electrical | Dedicated circuits for appliances
Electrical | Outlets for counters, island and exterior walls
Electrical | Low voltage: data, TV, doorbell, cameras, speakers
Electrical | Smoke and CO detector locations
Plumbing and gas | Supply and drains placed for the fixtures ordered
Plumbing and gas | Toilet distance from the wall
Plumbing and gas | Shower valve and head heights
Plumbing and gas | Tub and shower set, level and protected
Plumbing and gas | Pressure test passed, no drips or stains
Plumbing and gas | Nail plates where pipes are close to the stud face
Plumbing and gas | Gas lines capped and tested
Plumbing and gas | Washer box, ice maker line and hose bibs
Heating, cooling and ventilation | Ducts connected, sealed and supported
Heating, cooling and ventilation | No crushed or kinked flex duct
Heating, cooling and ventilation | Registers and returns where planned
Heating, cooling and ventilation | Bath fans, range hood and dryer vented outside
Photos | Every wall of every room, floor to ceiling
Photos | Tape measure in the frame at a known height
Photos | Corners and ceilings
Photos | Photos labeled by room
Sign-off | Fix items on a punch list with who and when
Sign-off | Fix items re-checked
Sign-off | Cleared for insulation and drywall
Free template from fieldpix.org. FieldPix can write this for you from a walkthrough on site.