## Renovation checklist
Job / address
Homeowner
Contractor
Start date
Section | Check | Result | Notes | Photo #
Plan and scope | Scope written room by room
Plan and scope | Selections made: fixtures, tile, cabinets, counters, appliances
Plan and scope | Lead times checked
Plan and scope | Budget with a contingency
Plan and scope | Drawings or plans if needed
Contract and paperwork | Written contract with scope, price and dates
Contract and paperwork | Payment schedule tied to milestones
Contract and paperwork | Change order process agreed
Contract and paperwork | License and insurance checked
Contract and paperwork | Permits: who pulls them, which inspections
Contract and paperwork | Lien waivers with payments, where used
Before work starts | Photos of existing conditions, inside and out
Before work starts | Floor protection and dust walls
Before work starts | Working hours, parking, dumpster and materials
Before work starts | Crew bathroom, keys and codes
Before work starts | Water, gas and electrical shut-offs located
Before work starts | Lead-safe rules if built before 1978; asbestos tested if needed
Demolition and rough-in | Surprises photographed
Demolition and rough-in | Changes signed before the extra work
Demolition and rough-in | Rough inspections passed
Demolition and rough-in | Pre-drywall walk done
Finishes | Deliveries checked on arrival
Finishes | Finishes match the selections
Finishes | Finished surfaces protected
Close-out | Punch list walked and agreed
Close-out | Punch list complete
Close-out | Final inspections passed, permits closed
Close-out | Manuals, warranties and paint colors handed over
Close-out | Final cleaning
Close-out | Final payment and final lien waiver
Close-out | After photos from the same spots as before
Free template from fieldpix.org. FieldPix can write this for you from a walkthrough on site.